## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | Issue Type 2-1 | Programme | 2026/07/17 13:12:00 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2026/07/17 13:28:14 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/f4e9e160-cd75-4562-bdb5-8d3d2859497a202607171328140000/Sectional/poua1c81f4a-e0f5-4cd8-a3af-a724899a75d5.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/f4e9e160-cd75-4562-bdb5-8d3d2859497a202607171328140000/Plan/ | MF | (none) | / | 2026/07/17 13:12:00 | 23
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/17 13:39:31 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/68d3b758-2862-4d1c-91a2-3404caef9db7202607171339310000/Sectional/pou5d938bdf-9cc1-4dc0-bc19-ebb32cdb5889.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/68d3b758-2862-4d1c-91a2-3404caef9db7202607171339310000/Plan/ | MF | (none) | / | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/17 15:10:28 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Sectional/pouf1dc8bd8-9132-4e3f-824a-11b4888e4a5a.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Plan/ | MF | (none) | / | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/17 15:10:28 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Sectional/poua56f41f4-e740-4a60-abd2-e5f64c787c6c.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Plan/ | MF | (none) | / | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/20 11:17:06 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Sectional/poubb545c64-3d55-48e9-9e79-c27c0fe39205.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-5 | new Programme | 2026/07/17 18:23:00 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2026/07/20 11:17:06 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Sectional/pou3d373a48-5de9-4047-80e4-7963c7947cfe.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Plan/ | MF | Hall 23 | / | 2026/07/17 11:12:00 | 10
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/20 16:26:42 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Sectional/poufb1b635c-51c3-4943-ac6c-ba9590faeed3.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/20 16:26:42 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Sectional/pou908a1d3b-c9bd-4f24-b2a6-53307f69b4dd.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/23 13:17:19 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Sectional/pou4a3aa226-82e0-42c0-beed-aaccf1a40ce3.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/23 13:17:19 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Sectional/poua4fc105e-e269-4819-8c32-aa36b1219765.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/pou2b0a4a37-8e60-457b-ad65-719e68a7af19.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-5 | new Programme | 2026/07/17 18:23:00 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/poue2e56945-7d7f-49fc-b5de-cca3de97b3f6.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 11:12:00 | 10
3 | Issue Type 4-2 | Programme | 2026/07/17 11:48:00 | 2 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/poue4b55e91-515f-433f-801e-436ca82f215d.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 11:48:00 | 10
4 | Issue Type 2-1 | Programme | 2026/07/17 13:12:00 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/poucadc88e7-4090-4844-a4af-24704a44ec6b.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 13:12:00 | 23
5 | Issue Type 2-2 | Programme | 2026/07/17 13:16:00 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/pou6f2ae742-9d82-4fe1-861d-ab187ac955e2.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 13:16:00 | 10
1 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/30 16:03:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/6a8d0260-65ec-41af-9cff-f0866cfbca36202607301603156120/Sectional/poucdc6e06c-ea45-4939-90b3-27e8e49bdaac.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/6a8d0260-65ec-41af-9cff-f0866cfbca36202607301603156120/Plan/(none) | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-5 | new Programme | 2026/07/17 18:23:00 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2026/07/30 16:03:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/6a8d0260-65ec-41af-9cff-f0866cfbca36202607301603156120/Sectional/pouc5031426-e6d1-42d3-95c8-36a16c2d6aeb.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/6a8d0260-65ec-41af-9cff-f0866cfbca36202607301603156120/Plan/(none) | MF | Hall 23 | / | 2026/07/17 11:12:00 | 10
1 | Issue Type 2-2 | Programme | 2026/07/17 13:16:00 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 2026/08/03 13:30:57 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/29e84b94-9428-48df-ac46-27131cd8bdf9202608031330573835/Sectional/pou255d9bb2-460f-4bc8-85d0-2f98609ac72c.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/29e84b94-9428-48df-ac46-27131cd8bdf9202608031330573835/Plan/(none) | MF | Hall 23 | / | 2026/07/17 13:16:00 | 10
1 | TYPE C | Programme1 | 2026/07/16 17:45:00 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2026/08/03 18:19:38 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/916a9352-e7b4-4ecd-b8a0-2572dbbfafab202608031819384124/Sectional/pouf144aacf-2a5b-4811-8b7c-6d00b2b76fb3.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/916a9352-e7b4-4ecd-b8a0-2572dbbfafab202608031819384124/Plan/(none) | MF | (none) | / | 2026/07/16 17:42:00 | 10
1 | TYPE_F | Programme | 2026/07/16 17:47:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026/08/03 18:20:14 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/de1c73f6-1ad9-45d0-bc24-02ff01651539202608031820140811/Sectional/pou1cc186c9-f3f0-480b-8516-8b3df7893a04.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/de1c73f6-1ad9-45d0-bc24-02ff01651539202608031820140811/Plan/(none) | MF | (none) | / | 2026/07/16 17:47:00 | 10
1 | TYPE C | Programme1 | 2026/07/16 17:45:00 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2026/08/04 08:54:28 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/fe9ab14e-0e8d-4e5a-aff1-4016cf9d92df202608040854282411/Sectional/pou24cc39c7-31bd-4b7e-b0c5-0bd66961b57e.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/fe9ab14e-0e8d-4e5a-aff1-4016cf9d92df202608040854282411/Plan/(none) | MF | (none) | / | 2026/07/16 17:42:00 | 10
1 | TYPE_F | Programme | 2026/07/16 17:47:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026/08/04 08:56:10 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/2f2b789b-4c6a-43b3-b2b6-bae6e7271a55202608040856104445/Sectional/pou58359a93-799f-481c-97b1-4eae1420a505.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/2f2b789b-4c6a-43b3-b2b6-bae6e7271a55202608040856104445/Plan/(none) | MF | (none) | / | 2026/07/16 17:47:00 | 10
1 | TYPE C | Programme1 | 2026/07/16 17:45:00 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2026/08/04 11:45:31 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/e39649a3-36fa-4808-928e-64751a619924202608041145313852/Sectional/poud60c1927-8b25-4fc8-a5ce-e5f0f809e7d3.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/e39649a3-36fa-4808-928e-64751a619924202608041145313852/Plan/(none) | MF | Hall 22 | / | 2026/07/16 17:42:00 | 10
2 | TYPE_F | Programme | 2026/07/16 17:47:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026/08/04 11:45:31 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/e39649a3-36fa-4808-928e-64751a619924202608041145313852/Sectional/pou8780287a-4335-4d13-aaa4-47e4934b68e7.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/e39649a3-36fa-4808-928e-64751a619924202608041145313852/Plan/(none) | MF | Hall 22 | / | 2026/07/16 17:47:00 | 10
1 | TYPE C | Programme1 | 2026/07/16 17:45:00 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou6e687efd-8fa3-4c70-a760-a60ea0bc0324.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/16 17:42:00 | 10
2 | TYPE_F | Programme | 2026/07/16 17:47:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou006a3401-d6b7-4116-9f99-b07a464cda58.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/16 17:47:00 | 10
3 | Issue Type 6-1 | Programme2 | 2026/07/17 09:01:00 | 0 | 0 | 1 | 1 | 0 | 4 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou78f026bb-24fc-40db-af21-8f34337a167c.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 08:56:00 | 10
4 | Issue Type 6-2 | Programme | 2026/07/17 09:03:00 | 0 | 0 | 1 | 1 | 1 | 18 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/poufd5dcada-9799-491f-abfe-8e80461946a7.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 09:03:00 | 10
5 | Issue Type 6-3 | Programme | 2026/07/17 09:19:00 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou75d3b437-f9d6-4b97-9485-c462bd1190a8.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 09:19:00 | 10
6 | Issue Type 1-2 | Programme | 2026/07/17 09:25:00 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/poue126002c-b2d3-4227-9386-421a312fa348.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 09:25:00 | 10
7 | Issue Type 4-1 | Programme | 2026/07/17 09:31:00 | 2 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou442f2ded-d7bf-4cec-ab9e-246fd01dc6da.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 09:31:00 | 10
8 | Issue Type 5-2 | Programme | 2026/07/17 09:40:00 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou8a2964a0-0ef5-4f11-95c9-cfe2f712b6f7.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 09:40:00 | 10
9 | Issue Type 7-3 | Programme | 2026/07/17 09:47:00 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 0 | 2026/08/04 12:28:15 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Sectional/pou91360030-b5b6-44f3-88ef-371ba98c44f6.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/d2252bd9-79c7-44d9-bd97-3659fcc29707202608041228157308/Plan/(none) | MF | Hall 22 | / | 2026/07/17 09:47:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.

## Sheet3
剖面号 | 方案号 | Ele ID | Time
Issue Type 7-4 | Option 2 | 22658486 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658489 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658491 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658493 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658495 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658497 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658501 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658503 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658506 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658509 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658514 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658518 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658522 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658526 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658530 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658533 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658535 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658537 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658539 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658541 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658543 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658545 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658548 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658550 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658553 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658556 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658559 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658562 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658564 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658567 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658569 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658571 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658573 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658576 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658579 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658581 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658584 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658587 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658590 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658592 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658595 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22673130 | 2026/07/30 16:03:15
Issue Type 7-4 | Option 2 | 22673134 | 2026/07/30 16:03:15
Issue Type 7-4 | Option 2 | 22673137 | 2026/07/30 16:03:15
Issue Type 7-4 | Option 2 | 22673140 | 2026/07/30 16:03:15
Issue Type 7-4 | Option 2 | 22673143 | 2026/07/30 16:03:15
Issue Type 7-5 | new Programme | 22673146 | 2026/07/30 16:03:15
Issue Type 7-5 | new Programme | 22673150 | 2026/07/30 16:03:15
Issue Type 7-5 | new Programme | 22673153 | 2026/07/30 16:03:15
Issue Type 7-5 | new Programme | 22673156 | 2026/07/30 16:03:15
Issue Type 2-2 | Programme | 22681333 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681336 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681339 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681342 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681345 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681348 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681351 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681354 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681357 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681360 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681363 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681366 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681369 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681372 | 2026/08/03 13:30:57
Issue Type 2-2 | Programme | 22681375 | 2026/08/03 13:30:57
TYPE C | Programme1 | 22878003 | 2026/08/03 18:19:38
TYPE C | Programme1 | 22878007 | 2026/08/03 18:19:38
TYPE_F | Programme | 22878011 | 2026/08/03 18:20:14
TYPE C | Programme1 | 22878077 | 2026/08/04 08:54:28
TYPE C | Programme1 | 22878082 | 2026/08/04 08:54:28
TYPE_F | Programme | 22878087 | 2026/08/04 08:56:10
TYPE C | Programme1 | 22879487 | 2026/08/04 11:45:31
TYPE C | Programme1 | 22879492 | 2026/08/04 11:45:31
TYPE_F | Programme | 22879497 | 2026/08/04 11:45:31
TYPE C | Programme1 | 22879576 | 2026/08/04 12:28:15
TYPE C | Programme1 | 22879581 | 2026/08/04 12:28:15
TYPE_F | Programme | 22879586 | 2026/08/04 12:28:15
Issue Type 6-1 | Programme2 | 22879590 | 2026/08/04 12:28:15
Issue Type 6-1 | Programme2 | 22879594 | 2026/08/04 12:28:15
Issue Type 6-1 | Programme2 | 22879599 | 2026/08/04 12:28:15
Issue Type 6-1 | Programme2 | 22879602 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879605 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879610 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879614 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879617 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879621 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879623 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879625 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879627 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879629 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879631 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879633 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879635 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879637 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879639 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879641 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879644 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879646 | 2026/08/04 12:28:15
Issue Type 6-2 | Programme | 22879648 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879650 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879655 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879659 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879663 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879667 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879671 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879674 | 2026/08/04 12:28:15
Issue Type 6-3 | Programme | 22879677 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879680 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879683 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879686 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879689 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879692 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879695 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879698 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879701 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879704 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879707 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879710 | 2026/08/04 12:28:15
Issue Type 1-2 | Programme | 22879712 | 2026/08/04 12:28:15
Issue Type 4-1 | Programme | 22879715 | 2026/08/04 12:28:15
Issue Type 4-1 | Programme | 22879720 | 2026/08/04 12:28:15
Issue Type 4-1 | Programme | 22879724 | 2026/08/04 12:28:15
Issue Type 4-1 | Programme | 22879729 | 2026/08/04 12:28:15
Issue Type 4-1 | Programme | 22879734 | 2026/08/04 12:28:15
Issue Type 5-2 | Programme | 22879737 | 2026/08/04 12:28:15
Issue Type 5-2 | Programme | 22879740 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879743 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879747 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879750 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879753 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879756 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879759 | 2026/08/04 12:28:15
Issue Type 7-3 | Programme | 22879762 | 2026/08/04 12:28:15