## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | Issue Type 2-1 | Programme | 2026/07/17 13:12:00 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2026/07/17 13:28:14 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/f4e9e160-cd75-4562-bdb5-8d3d2859497a202607171328140000/Sectional/poua1c81f4a-e0f5-4cd8-a3af-a724899a75d5.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/f4e9e160-cd75-4562-bdb5-8d3d2859497a202607171328140000/Plan/ | MF | (none) | / | 2026/07/17 13:12:00 | 23
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/17 13:39:31 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/68d3b758-2862-4d1c-91a2-3404caef9db7202607171339310000/Sectional/pou5d938bdf-9cc1-4dc0-bc19-ebb32cdb5889.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/68d3b758-2862-4d1c-91a2-3404caef9db7202607171339310000/Plan/ | MF | (none) | / | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/17 15:10:28 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Sectional/pouf1dc8bd8-9132-4e3f-824a-11b4888e4a5a.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Plan/ | MF | (none) | / | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/17 15:10:28 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Sectional/poua56f41f4-e740-4a60-abd2-e5f64c787c6c.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/ada065af-cc6a-43e4-ad7a-75f5ac4fc4ca202607171510280000/Plan/ | MF | (none) | / | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/20 11:17:06 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Sectional/poubb545c64-3d55-48e9-9e79-c27c0fe39205.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-5 | new Programme | 2026/07/17 18:23:00 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2026/07/20 11:17:06 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Sectional/pou3d373a48-5de9-4047-80e4-7963c7947cfe.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/8da44dd1-81c6-4825-95ca-911e8109a67b202607201117060000/Plan/ | MF | Hall 23 | / | 2026/07/17 11:12:00 | 10
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/20 16:26:42 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Sectional/poufb1b635c-51c3-4943-ac6c-ba9590faeed3.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/20 16:26:42 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Sectional/pou908a1d3b-c9bd-4f24-b2a6-53307f69b4dd.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1ee33952-9b61-4ca8-ab78-95b291bb6d61202607201626420000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Programme | 2026/07/17 11:07:00 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/23 13:17:19 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Sectional/pou4a3aa226-82e0-42c0-beed-aaccf1a40ce3.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/23 13:17:19 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Sectional/poua4fc105e-e269-4819-8c32-aa36b1219765.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/edc33e55-8dba-4d16-9280-c453defb80bd202607231317190000/Plan/ | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
1 | Issue Type 7-4 | Option 2 | 2026/07/17 15:08:00 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/pou2b0a4a37-8e60-457b-ad65-719e68a7af19.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | 4A-5/H-1-H-2 | 2026/07/17 11:07:00 | 11
2 | Issue Type 7-5 | new Programme | 2026/07/17 18:23:00 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/poue2e56945-7d7f-49fc-b5de-cca3de97b3f6.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 11:12:00 | 10
3 | Issue Type 4-2 | Programme | 2026/07/17 11:48:00 | 2 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/poue4b55e91-515f-433f-801e-436ca82f215d.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 11:48:00 | 10
4 | Issue Type 2-1 | Programme | 2026/07/17 13:12:00 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/poucadc88e7-4090-4844-a4af-24704a44ec6b.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 13:12:00 | 23
5 | Issue Type 2-2 | Programme | 2026/07/17 13:16:00 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 2026/07/24 14:53:48 | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Sectional/pou6f2ae742-9d82-4fe1-861d-ab187ac955e2.png | https://transit.szhoogo.com/0c150dd0-780d-4c46-921e-14f52b2cc2b7/1e6f4b18-b144-4f58-80c1-66c49d7d5575202607241453485627/Plan/(none) | MF | Hall 23 | / | 2026/07/17 13:16:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.

## Sheet3
剖面号 | 方案号 | Ele ID | Time
Issue Type 7-4 | Option 2 | 22658486 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658489 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658491 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658493 | 2026/07/24 14:53:48
Issue Type 7-4 | Option 2 | 22658495 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658497 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658501 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658503 | 2026/07/24 14:53:48
Issue Type 7-5 | new Programme | 22658506 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658509 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658514 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658518 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658522 | 2026/07/24 14:53:48
Issue Type 4-2 | Programme | 22658526 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658530 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658533 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658535 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658537 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658539 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658541 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658543 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658545 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658548 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658550 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658553 | 2026/07/24 14:53:48
Issue Type 2-1 | Programme | 22658556 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658559 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658562 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658564 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658567 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658569 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658571 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658573 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658576 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658579 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658581 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658584 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658587 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658590 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658592 | 2026/07/24 14:53:48
Issue Type 2-2 | Programme | 22658595 | 2026/07/24 14:53:48