## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | TYPE541 | CSD待更新 | 2026/01/29 08:33:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:34 | https://transit.szhoogo.com/20260422.cheshi/533CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | D-E/1-2 | 2026/01/29 08:33:00 | 10
2 | TYPE542 | CSD待更新 | 2026/01/29 08:33:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:34 | https://transit.szhoogo.com/20260422.cheshi/533CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | D-E/1-2 | 2026/01/29 08:33:00 | 10
3 | TYPE543 | CSD待更新 | 2026/01/29 08:33:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:34 | https://transit.szhoogo.com/20260422.cheshi/533CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | D-E/1-2 | 2026/01/29 08:33:00 | 10
1 | CSD_533 | CSD待更新 | 2026/01/29 08:33:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/533CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | D-E/1-2 | 2026/01/29 08:33:00 | 10
2 | CSD_534 | CSD待更新 | 2026/01/29 08:33:01 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/534CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | B3F(-13.15m) | CL | 28-29/C-D | 2025/03/03 11:10:00 | 10
3 | CSD_535 | CSD待更新 | 2026/01/29 08:33:02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/535CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | D-E/1-2 | 2026/01/29 08:33:00 | 10
4 | CSD_536 | CSD待更新 | 2026/01/29 08:33:03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/536CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | 28-29/C-D | 2025/03/03 11:10:00 | 10
5 | CSD_537 | CSD待更新 | 2026/01/29 08:33:04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/537CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | D-E/1-2 | 2026/01/29 08:33:00 | 10
6 | CSD_538 | CSD待更新 | 2026/01/29 08:33:05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/538CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | 28-29/C-D | 2025/03/03 11:10:00 | 10
7 | CSD_539 | CSD待更新 | 2026/01/29 08:33:06 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:52 | https://transit.szhoogo.com/20260422.cheshi/539CSD待更新.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | CL | 28-29/C-D | 2025/03/03 11:10:00 | 10
1 | CSD_1 | Programme | 2026/01/29 08:33:00 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2026/01/29 09:03:53 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Sectional/pou83fdfaaf-c092-4b3d-954a-7c7e5c39d977.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/62230aad-1d75-4c23-a69e-17704e286510202601290903520000/Plan/pin_ff10add1-1da7-48f0-a449-b8c92c80dae1.png | B3F(-13.15m) | (none) | D-E/1-2 | 2026/01/29 08:33:00 | 10
1 | Type18-1 | CSD待更新 | 2025/05/15 11:59:00 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou45c12428-6a3a-43e3-88b9-db09f96190e7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 28-29/C-D | 2025/03/03 11:10:00 | 10
2 | Type18-3 | CSD待更新 | 2025/05/15 11:59:00 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poude06e7cc-0b9d-4841-9e4e-163e70e3d8e7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 32-33/C-D | 2025/03/04 16:35:00 | 10
3 | Type20_1F | new Programme | 2025/05/17 02:08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou9821e023-786e-4ba1-9bce-e6ea905da001.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 33-34/F | 2025/03/06 14:31:00 | 10
4 | Type20_2 | new Programme | 2025/05/17 02:09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou61ec4314-213b-480d-ae77-e7eb1582938a.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 34-35/F | 2025/03/06 16:20:00 | 10
5 | Type20_3F | new Programme | 2025/05/17 02:14:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou27f0e1ba-eb85-405f-b6ba-2fdd91ff909c.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 34-35/F | 2025/03/07 09:35:00 | 10
6 | Type19_1F | new Programme | 2025/05/17 02:02:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou97117bd3-c2a5-41bb-a9fc-974f5f240fc1.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 34-35/F | 2025/03/07 09:41:00 | 10
7 | Type19_2F | new Programme | 2025/05/17 02:03:00 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou76641650-f73c-46d0-898b-588c4b8cd52b.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | D-E/34-35 | 2025/03/07 09:43:00 | 10
8 | Type13-1_1F | CSD待更新 | 2025/05/15 12:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouccb2d3f5-c35a-4c23-9457-bc6fc6a0f4fe.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 11-12/EC-ED | 2025/03/07 10:24:00 | 10
9 | Type13-2_1 | new Programme | 2025/05/17 01:58:00 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouc2c8e258-fce5-4cad-91b2-6b233055a9af.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 12-13/E-F | 2025/03/07 11:07:00 | 10
10 | Type13-2_2F | new Programme | 2025/05/17 02:01:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou515240f2-c104-4e49-9388-a49561c71278.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 13-14/E-F | 2025/03/07 11:12:00 | 10
11 | Type12-1 | new Programme | 2025/05/20 10:30:00 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou0f6d7fc7-38b5-4b95-9238-cee7ed470c08.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 12-13/A-B | 2025/03/07 11:50:00 | 10
12 | Type12-2 | new Programme | 2025/05/19 16:44:00 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouc3f4fadf-969d-496a-80ed-75adcf47744b.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 13-14/A-B | 2025/03/07 11:53:00 | 10
13 | Type16-2 | CSD待更新 | 2025/05/15 12:03:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poud8b2ba43-e713-4031-8515-87fae44e6c0f.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 21-22/A-B | 2025/03/07 14:56:00 | 10
14 | Type14-1 | CSD待更新 | 2025/05/15 12:03:00 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poucdcdb556-6e5c-420a-9bb7-2caa94089778.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 14-15/A-B | 2025/03/07 15:08:00 | 10
15 | Type14-2 | CSD待更新 | 2025/05/15 12:03:00 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou2a549db4-7456-40ab-a774-358ed1d2df7f.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 18-19/A-B | 2025/03/07 15:13:00 | 10
16 | Type15-1 | CSD待更新 | 2025/05/15 12:03:00 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou4bf94559-456d-47fa-b379-3a11244270e8.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 14-15/B-C | 2025/03/07 15:23:00 | 10
17 | Type11-1F | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poubf637527-a98b-43cf-902c-db2f8a5134e2.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 9-10/B-C | 2025/03/07 16:03:00 | 10
18 | Type11-2 | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poud1047a54-c87a-4d16-980d-a933313651d7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 11-12/B-C | 2025/03/07 16:08:00 | 10
19 | Type10F | CSD待更新 | 2025/05/15 12:05:00 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou6ea347bd-6fe7-44da-9c91-bac790c426d2.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 9-10/D-F | 2025/03/07 16:15:00 | 10
20 | Type8-1F | new Programme | 2025/05/16 20:54:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou239a3cde-31df-46da-91f4-6a97e4872f23.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 5-6/C-D | 2025/03/07 16:25:00 | 10
21 | Type8-2F | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouef830330-d407-4829-a4de-35bedad89999.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 8-9/C-D | 2025/03/07 16:51:00 | 10
22 | Type9-6 | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouc827fc15-4439-4524-93f2-1d09b65923fd.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 5-6/E-F | 2025/03/07 17:25:00 | 10
23 | Type9-1 | CSD待更新 | 2025/05/15 12:06:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poua58feea6-c1b6-4c08-9698-24cfa16f667a.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 6-7/EC-ED | 2025/03/07 17:49:00 | 10
24 | Type7-5 | new Programme | 2025/05/16 17:16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou3d2dded6-c12c-48d4-a4a8-ce8ebb467ef9.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 3-4/E-F | 2025/03/07 18:23:00 | 10
25 | Type7-2 | new Programme | 2025/05/16 19:29:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poua5196a58-ebec-4b68-b158-c0a188bd63d3.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 3-4/E-F | 2025/03/07 18:25:00 | 10
26 | Type1-1 | new Programme | 2025/05/21 11:16:00 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou3e8b01a4-a32b-4178-b9a1-1adc27bb5dfd.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 2-3/B-C | 2025/03/09 15:02:00 | 10
27 | Type1-2 | CSD待更新 | 2025/05/15 12:08:00 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou3fcc90cd-06c2-4897-b35d-b390580d054f.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 5-6/B-C | 2025/03/09 15:06:00 | 10
28 | Type2-1 | CSD待更新 | 2025/05/15 12:08:00 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou5a7ae5d2-f732-4ef2-84fe-af129b981afb.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 5-6/C-D | 2025/03/09 15:48:00 | 10
29 | Type2-7 | CSD待更新 | 2025/05/15 12:08:00 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou0483ee4b-6d7a-43b8-82de-23e4ae252576.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 8-9/C-E | 2025/03/09 16:23:00 | 10
30 | Type3-1 | new Programme | 2025/05/21 14:22:00 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouc4161579-1ac3-43eb-94ac-4d19f5f4cccd.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 8-9/D-E | 2025/03/09 16:44:00 | 10
31 | Type5-1 | new Programme | 2025/05/21 14:44:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poue167f38a-282d-4d34-83e6-93db88eabbd7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 10-11/C-E | 2025/03/10 00:08:00 | 10
32 | Type5-4 | new Programme | 2025/05/21 14:49:00 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou0d287a88-9f13-451c-a53a-a66f6b493dab.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 18-19/C-E | 2025/03/10 00:12:00 | 10
33 | Type5-5 | new Programme | 2026/02/11 14:08:00 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poueeaa71e6-2d4d-4bdc-987d-417db54c2ab1.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 124-25/C-E | 2025/03/10 00:12:00 | 10
34 | Type4-2 | new Programme | 2025/05/21 14:34:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou3f8b561c-6014-46bd-8129-de13af973bb4.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 25/A | 2025/03/10 00:55:00 | 10
35 | Type4-5 | new Programme | 2026/02/11 14:10:00 | 0 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouda9b40de-d0fe-4b43-899b-b998cd015982.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 25/A | 2025/03/10 00:56:00 | 10
36 | Type4-11 | new Programme | 2025/05/21 14:41:00 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou6b904551-1654-4595-9f50-d5246ff92ed4.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | PLATFORM LEVEL | PL | 25/A | 2025/03/10 00:56:00 | 10
37 | Type26-1 | 待工程師審核 | 2025/05/15 12:10:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou48659eb8-b8bb-4d43-981a-8849e4c9d6ec.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL (OVERALL) | GL | D1-D2/CC-DD | 2025/03/18 13:55:00 | 10
38 | Type26-2 | 待工程師審核 | 2025/05/15 12:10:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou65c59eba-c056-43cd-94f0-df1146039071.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL (OVERALL) | GL | D1-D2/CC-DD | 2025/03/18 14:14:00 | 10
39 | Type24-30 | 待工程師審核 | 2025/05/15 12:10:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou59a3adb8-8c7f-4e20-9c48-3006d4900987.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL (OVERALL) | GL | E4-E5/EA-EB | 2025/03/18 15:34:00 | 10
40 | Type24-2 | 待工程師審核 | 2025/05/15 12:11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poudcd4fc20-b65e-4cd4-bae8-714c3b35cc08.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL (OVERALL) | GL | E4-E5/EB | 2025/03/18 15:58:00 | 10
41 | Type33-2 | 待工程師審核 | 2025/05/15 12:11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou13ab678f-e26a-460a-92ce-1c6141d6b0e4.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | North Vent Shaft First Level | FL | D1-D2/CC-DD | 2025/03/19 12:29:00 | 10
42 | Type21-1 | 待工程師審核 | 2025/05/15 12:11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouc89846f3-60a0-4c86-a92f-b81a547fdff6.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL | GL | E1-E2/EC-ED | 2025/03/09 16:05:00 | 10
43 | Type33-1 | 待工程師審核 | 2025/05/15 12:12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pouf0c4d742-4f9a-4885-af9b-957ddb0311ac.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | North Vent Shaft First Level | FL | D1-D2/CC-DD | 2025/03/27 01:14:00 | 10
44 | Type18-2 | CSD待更新 | 2025/05/15 12:12:00 | 0 | 2 | 1 | 10 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou90a47166-2abe-409f-87c1-27a6df3c2049.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 31-32/C-D | 2025/03/04 16:23:00 | 10
45 | Type22-2 | 待工程師審核 | 2025/05/15 12:12:00 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou8776aa17-1ac8-4e4a-85a1-56b1e182cb9e.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL | GL | 7-8/X15 | 2025/05/12 16:00:00 | 10
46 | Type22-1 | 待工程師審核 | 2025/05/15 12:12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou8ee8f120-972b-4ef5-b0a9-c33e376c951e.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL | GL | 7-8/X15 | 2025/05/12 16:00:00 | 10
47 | Type23 | 待工程師審核 | 2025/05/15 12:12:00 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou77451786-d745-4e77-975c-152917027882.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | GROUND LEVEL | GL | ED-EC/E2-E3 | 2025/05/12 16:36:00 | 10
48 | Type31-2 | 待工程師審核 | 2025/05/15 12:13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/pou39a73da5-d73a-4419-bcbf-ad92b2e1ac4a.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | North Vent Shaft First Level | FL | A1-A2/AB | 2025/03/27 00:40:00 | 10
49 | Type32 | 待工程師審核 | 2025/05/14 11:48:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poud4d9b5d2-f6ef-41ee-b38e-c11537cba6c0.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | North Vent Shaft First Level | FL | A1-A2/AB | 2025/05/14 11:44:00 | 10
50 | Type7-1 | new Programme | 2025/05/21 11:51:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:00:05 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Sectional/poue024e058-c717-4258-90b0-04945132fb19.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/476c13a4-df05-4ec1-b6f4-2ac1c7fbefc1202602121400050000/Plan/ | CONCOURSE Level | CL | 3-4/E-F | 2025/05/16 18:51:00 | 10
1 | Type18-1 | CSD待更新 | 2025/05/15 11:59:00 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouf5c504e7-6ffd-4fb5-a3e2-eddd2d67571d.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 28-29/C-D | 2025/03/03 11:10:00 | 10
2 | Type18-3 | CSD待更新 | 2025/05/15 11:59:00 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou0a58192b-0e88-40ea-a4dc-f81fbf157a0c.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 32-33/C-D | 2025/03/04 16:35:00 | 10
3 | Type20_1F | new Programme | 2025/05/17 02:08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouebae7b9b-cfcd-48b4-a089-2da7d257b658.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 33-34/F | 2025/03/06 14:31:00 | 10
4 | Type20_2 | new Programme | 2025/05/17 02:09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poufa15981f-3e8f-4a25-95e2-bdeb36af4930.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 34-35/F | 2025/03/06 16:20:00 | 10
5 | Type20_3F | new Programme | 2025/05/17 02:14:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poua9ad4a91-5a9b-4a4e-b817-04288b07ad24.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 34-35/F | 2025/03/07 09:35:00 | 10
6 | Type19_1F | new Programme | 2025/05/17 02:02:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poufb32ebfd-6b3f-4283-917f-3992d7a7c91d.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 34-35/F | 2025/03/07 09:41:00 | 10
7 | Type19_2F | new Programme | 2025/05/17 02:03:00 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou1c1c9c4d-2b50-4851-8618-066ae10c6d69.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | D-E/34-35 | 2025/03/07 09:43:00 | 10
8 | Type13-1_1F | CSD待更新 | 2025/05/15 12:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poubcd9717c-2319-4116-b7b8-ca98cfeb8341.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 11-12/EC-ED | 2025/03/07 10:24:00 | 10
9 | Type13-2_1 | new Programme | 2025/05/17 01:58:00 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouc69080d7-b046-43dd-b42a-1770616424ec.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 12-13/E-F | 2025/03/07 11:07:00 | 10
10 | Type13-2_2F | new Programme | 2025/05/17 02:01:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poud6ea638d-ede8-4ed8-8494-d439543eca48.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 13-14/E-F | 2025/03/07 11:12:00 | 10
11 | Type12-1 | new Programme | 2025/05/20 10:30:00 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou4068e6da-aa9f-4c0c-ac83-37e0015406cb.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 12-13/A-B | 2025/03/07 11:50:00 | 10
12 | Type12-2 | new Programme | 2025/05/19 16:44:00 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou2067606b-5dd2-4316-8e2c-bbc3702348c7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 13-14/A-B | 2025/03/07 11:53:00 | 10
13 | Type16-2 | CSD待更新 | 2025/05/15 12:03:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou0fe3a6d7-684b-4393-b675-a323559cc487.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 21-22/A-B | 2025/03/07 14:56:00 | 10
14 | Type14-1 | CSD待更新 | 2025/05/15 12:03:00 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou454bb1a6-3252-4d49-a2b4-2d2fd5b86693.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 14-15/A-B | 2025/03/07 15:08:00 | 10
15 | Type14-2 | CSD待更新 | 2025/05/15 12:03:00 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poub5371a86-38a5-43c8-b4ef-309711e91cef.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 18-19/A-B | 2025/03/07 15:13:00 | 10
16 | Type15-1 | CSD待更新 | 2025/05/15 12:03:00 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouf3081447-f3c7-4aa2-a3bb-b83bb3d76170.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 14-15/B-C | 2025/03/07 15:23:00 | 10
17 | Type11-1F | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou71552a3f-ffa1-4c72-a458-4ec95370d9dc.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 9-10/B-C | 2025/03/07 16:03:00 | 10
18 | Type11-2 | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouf8068aba-7a16-4c23-8f83-94c0e501eded.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 11-12/B-C | 2025/03/07 16:08:00 | 10
19 | Type10F | CSD待更新 | 2025/05/15 12:05:00 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou168cc822-13cf-4fbe-91ce-45c1c04cdf89.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 9-10/D-F | 2025/03/07 16:15:00 | 10
20 | Type8-1F | new Programme | 2025/05/16 20:54:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poue3bc238b-dfa9-45d3-907b-d10053c1cf58.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 5-6/C-D | 2025/03/07 16:25:00 | 10
21 | Type8-2F | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouda4924ed-ee7e-4923-a79d-22f701162129.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 8-9/C-D | 2025/03/07 16:51:00 | 10
22 | Type9-6 | CSD待更新 | 2025/05/15 12:05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou5646252d-8b0a-4ca7-ab72-eb9354209fc9.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 5-6/E-F | 2025/03/07 17:25:00 | 10
23 | Type9-1 | CSD待更新 | 2025/05/15 12:06:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou0721c921-a3a3-4e3f-b4fb-e47046c2dbd1.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 6-7/EC-ED | 2025/03/07 17:49:00 | 10
24 | Type7-5 | new Programme | 2025/05/16 17:16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou7af5c0ef-337d-49f4-a920-ab1c3706c36b.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 3-4/E-F | 2025/03/07 18:23:00 | 10
25 | Type7-2 | new Programme | 2025/05/16 19:29:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou9455400e-9728-42e6-a832-a084bf18124c.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 3-4/E-F | 2025/03/07 18:25:00 | 10
26 | Type1-1 | new Programme | 2025/05/21 11:16:00 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou4dfa3491-20dc-48e6-a829-b4a44cf91e84.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 2-3/B-C | 2025/03/09 15:02:00 | 10
27 | Type1-2 | CSD待更新 | 2025/05/15 12:08:00 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou304418a8-3343-4604-91f0-39d1a65c1aaa.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 5-6/B-C | 2025/03/09 15:06:00 | 10
28 | Type2-1 | CSD待更新 | 2025/05/15 12:08:00 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouce313be3-b287-4453-8f58-d12ccdaf710e.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 5-6/C-D | 2025/03/09 15:48:00 | 10
29 | Type2-7 | CSD待更新 | 2025/05/15 12:08:00 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou9a75a636-a598-47ea-9de3-519042f1adf6.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 8-9/C-E | 2025/03/09 16:23:00 | 10
30 | Type3-1 | new Programme | 2025/05/21 14:22:00 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou1403000e-8c61-4f46-8aca-1fa454e1ace1.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 8-9/D-E | 2025/03/09 16:44:00 | 10
31 | Type5-1 | new Programme | 2025/05/21 14:44:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou17cfa6e9-3e4a-457f-9321-a2ffed105e38.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 10-11/C-E | 2025/03/10 00:08:00 | 10
32 | Type5-4 | new Programme | 2025/05/21 14:49:00 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou366297f4-b367-4a8f-84e2-bcbad6595bf3.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 18-19/C-E | 2025/03/10 00:12:00 | 10
33 | Type5-5 | new Programme | 2026/02/11 14:08:00 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou9456777d-39d5-4c0f-8fa3-e02d0fec15d1.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 124-25/C-E | 2025/03/10 00:12:00 | 10
34 | Type4-2 | new Programme | 2025/05/21 14:34:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou3425f695-384c-436c-9083-99fe784a480d.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 25/A | 2025/03/10 00:55:00 | 10
35 | Type4-5 | new Programme | 2026/02/11 14:10:00 | 0 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou7513dafd-a8f8-48db-9e4f-89ad86120f6f.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 25/A | 2025/03/10 00:56:00 | 10
36 | Type4-11 | new Programme | 2025/05/21 14:41:00 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou22a1be9c-ad71-44e6-b64c-d1bdebaf2c4e.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | PLATFORM LEVEL | PL | 25/A | 2025/03/10 00:56:00 | 10
37 | Type26-1 | 待工程師審核 | 2025/05/15 12:10:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou6c451b12-28b7-4bf9-ac42-72c5832dfd63.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL (OVERALL) | GL | D1-D2/CC-DD | 2025/03/18 13:55:00 | 10
38 | Type26-2 | 待工程師審核 | 2025/05/15 12:10:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poua9b4f524-df7b-4dca-9b84-5b9d9f7bc00e.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL (OVERALL) | GL | D1-D2/CC-DD | 2025/03/18 14:14:00 | 10
39 | Type24-30 | 待工程師審核 | 2025/05/15 12:10:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poub7a20ed5-c736-434d-a842-2d6e1bee700d.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL (OVERALL) | GL | E4-E5/EA-EB | 2025/03/18 15:34:00 | 10
40 | Type24-2 | 待工程師審核 | 2025/05/15 12:11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouf0f94dc3-547d-463b-99c7-a1a0c3d95613.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL (OVERALL) | GL | E4-E5/EB | 2025/03/18 15:58:00 | 10
41 | Type33-2 | 待工程師審核 | 2025/05/15 12:11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouacda2f46-f7b9-468c-93bb-2d77a23df2c7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | North Vent Shaft First Level | FL | D1-D2/CC-DD | 2025/03/19 12:29:00 | 10
42 | Type21-1 | 待工程師審核 | 2025/05/15 12:11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouda4a0ed7-e029-457d-9b9c-db342c858d4e.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL | GL | E1-E2/EC-ED | 2025/03/09 16:05:00 | 10
43 | Type33-1 | 待工程師審核 | 2025/05/15 12:12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pouf65d3333-2d0d-4eac-a95d-5d928a3c2bfa.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | North Vent Shaft First Level | FL | D1-D2/CC-DD | 2025/03/27 01:14:00 | 10
44 | Type18-2 | CSD待更新 | 2025/05/15 12:12:00 | 0 | 2 | 1 | 10 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou4a1aac41-177b-48eb-8558-a39832845587.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 31-32/C-D | 2025/03/04 16:23:00 | 10
45 | Type22-2 | 待工程師審核 | 2025/05/15 12:12:00 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poue9706152-ebf1-47b1-87bd-bfae3e86abd7.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL | GL | 7-8/X15 | 2025/05/12 16:00:00 | 10
46 | Type22-1 | 待工程師審核 | 2025/05/15 12:12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou267ec914-0f79-4cba-baa7-067864c5eef6.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL | GL | 7-8/X15 | 2025/05/12 16:00:00 | 10
47 | Type23 | 待工程師審核 | 2025/05/15 12:12:00 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/poue88a9317-db6f-4968-9f29-ec30b77ff12d.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | GROUND LEVEL | GL | ED-EC/E2-E3 | 2025/05/12 16:36:00 | 10
48 | Type31-2 | 待工程師審核 | 2025/05/15 12:13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou3965ec4e-d254-4cb8-88f3-bae591bcfd30.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | North Vent Shaft First Level | FL | A1-A2/AB | 2025/03/27 00:40:00 | 10
49 | Type32 | 待工程師審核 | 2025/05/14 11:48:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou1d8a7a44-d16c-4362-aaa0-c3c00f0657fa.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | North Vent Shaft First Level | FL | A1-A2/AB | 2025/05/14 11:44:00 | 10
50 | Type7-1 | new Programme | 2025/05/21 11:51:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026/02/12 14:07:28 | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Sectional/pou4ff075b6-bc15-4103-bbd2-a411cae3b3f8.png | https://transit.szhoogo.com/90adcd98-b4ce-45a2-9153-936c3feea7f6/8a8fc8ab-8fba-4ffc-ad75-aa51d631f3d5202602121407280000/Plan/ | CONCOURSE Level | CL | 3-4/E-F | 2025/05/16 18:51:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.