## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | CSD_1 | Programme copy | 2025/03/12 13:55:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou0d0545e3-d197-4b70-95b0-e62dd6383d66.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 50-51/D-E | 2025/03/12 13:54:00 | 10
2 | CSD_1-1 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou9aaba01c-cb31-46ac-baff-29d43658d5bd.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 51-52/D-E | 2025/04/21 16:30:00 | 10
3 | CSD_1-2 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou790171e6-bcc4-42f6-badf-3a227e6234d3.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 52-53/D-E | 2025/04/21 16:30:00 | 10
4 | CSD_1-3 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou83b86510-e55c-42e3-b34a-f84b456565ce.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 53-54/D-E | 2025/04/21 16:30:00 | 10
5 | CSD_1-4 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/poue519e134-8f08-4eef-85b3-1e8ce526eb27.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 54-55/D-E | 2025/04/21 16:30:00 | 10
6 | CSD_1-5 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou56eb3150-b885-41e6-9d49-60ffd1aea18e.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 55-56/D-E | 2025/04/21 16:30:00 | 10
7 | CSD_1-6 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/poud58098d3-e308-446e-ab85-72b60b780613.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 56-57/D-E | 2025/04/21 16:30:00 | 10
8 | CSD_1-7 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou411c5192-062b-489e-8d34-c4a0ebc17871.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 57-58/D-E | 2025/04/21 16:30:00 | 10
9 | CSD_1-8 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/poub9e3b02b-429d-4ecd-b699-5c0d75d85ba6.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 58-59/D-E | 2025/04/21 16:30:00 | 10
10 | CSD_1-9 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/pou39b4b104-6439-49cf-819e-995d0b54e7a9.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 59-60/D-E | 2025/04/21 16:30:00 | 10
11 | CSD_1-10 | Programme | 2025/04/21 16:30:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/22 09:32:44 | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Sectional/poud87204fa-9319-4cc3-82e2-9c4cc9934d06.png | https://transit.szhoogo.com/2215a184-640f-4c97-894f-8d39a0a8d5fe/6015eaa7-0273-4893-97ab-e2466d948644202504220932440000/Plan/(none) | T.O. 楼板 | (none) | 60-61/D-E | 2025/04/21 16:30:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.