## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | CSD_1 | Initial condition | 2026/08/13 09:36:00 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 2026/08/13 09:41:51 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Sectional/poua786b251-bec3-4068-8dc5-2fce0bdb969e.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Plan/(none) | 1F | (none) | 4-5/D | 2026/07/14 15:36:00 | 10
2 | CSD_2 | Initial condition | 2026/08/13 09:37:00 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 2026/08/13 09:41:51 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Sectional/poucd71819c-15b8-4816-b80a-892e62c2ee80.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Plan/(none) | 1F | (none) | 4-5/D | 2026/07/14 16:36:00 | 10
3 | CSD_3 | Initial condition | 2026/08/13 09:38:00 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 2026/08/13 09:41:51 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Sectional/poubff8fd41-0213-4d1d-a442-41e5c64b9122.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Plan/(none) | 1F | (none) | C-D/5-6 | 2026/07/14 17:13:00 | 10
4 | CSD_4 | Initial condition | 2026/08/13 09:38:00 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 2026/08/13 09:41:51 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Sectional/pou51a986b4-3bda-4e90-bab9-8f229476fedd.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Plan/(none) | 1F | (none) | B-C/5-6 | 2026/07/14 17:25:00 | 10
5 | CSD_5 | Initial condition | 2026/08/13 09:38:00 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 2026/08/13 09:41:51 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Sectional/pouee8ceb33-8732-4f2d-8d13-af5576c17e53.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Plan/(none) | 1F | (none) | 4-5/B-C | 2026/07/15 11:06:00 | 10
6 | CSD_6 | Initial condition | 2026/08/13 09:39:00 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 2026/08/13 09:41:51 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Sectional/poua9d72d73-e8e7-4383-95e6-77d609bd9780.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/db2a6db7-142f-4380-9147-d3c5f71196b1202608130941512021/Plan/(none) | 1F | (none) | 4-5/B-C | 2026/07/15 14:08:00 | 10
1 | CSD_1 | Option 1 | 2026/07/21 12:01:00 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 2026/08/17 16:21:48 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Sectional/pou1e85acb5-fd91-4e64-9ebe-956c5ed8981a.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Plan/(none) | 1F | (none) | 4-5/D | 2026/07/14 15:36:00 | 10
2 | CSD_2 | Option 1 | 2026/07/21 13:29:00 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 2026/08/17 16:21:48 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Sectional/poue90696e2-ad31-4938-a6cd-5c952c2fd520.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Plan/(none) | 1F | (none) | 4-5/D | 2026/07/14 16:36:00 | 10
3 | CSD_3 | Option 1 | 2026/07/21 15:39:00 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2026/08/17 16:21:48 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Sectional/pouf6e40998-18d2-4f28-9bb8-f2ea16629269.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Plan/(none) | 1F | (none) | C-D/5-6 | 2026/07/14 17:13:00 | 10
4 | CSD_4 | Option 1 | 2026/07/21 15:03:00 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 2026/08/17 16:21:48 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Sectional/pouaf448878-4bd4-4c6c-934e-d1cb2877b90d.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Plan/(none) | 1F | (none) | B-C/5-6 | 2026/07/14 17:25:00 | 10
5 | CSD_5 | Option 1 | 2026/07/21 15:21:00 | 0 | 0 | 0 | 0 | 0 | 27 | 2 | 0 | 2026/08/17 16:21:48 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Sectional/pou27a32457-36c7-46e9-886d-31e4ef599b23.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Plan/(none) | 1F | (none) | 4-5/B-C | 2026/07/15 11:06:00 | 10
6 | CSD_6 | Option 1 | 2026/07/21 13:24:00 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 0 | 2026/08/17 16:21:48 | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Sectional/pou5cdbea93-2828-4e50-b845-bab60e9d6aed.png | https://transit.szhoogo.com/8789bf61-005c-4663-ac6a-48c1ec821ff4/0f8275e1-d4df-451f-aca0-c6be0b2ead00202608171621480995/Plan/(none) | 1F | (none) | 4-5/B-C | 2026/07/15 14:08:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.

## Sheet3
剖面号 | 方案号 | Ele ID | Time
CSD_1 | Initial condition | 5867126 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867130 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867134 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867136 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867138 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867141 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867144 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867146 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867148 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867150 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867153 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867155 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867157 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867160 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867162 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867164 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867166 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867168 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867170 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867172 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867174 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867178 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867182 | 2026/08/13 09:41:51
CSD_1 | Initial condition | 5867186 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867190 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867195 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867200 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867205 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867208 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867211 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867214 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867218 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867221 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867224 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867227 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867230 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867233 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867236 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867240 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867243 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867246 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867249 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867252 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867255 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867258 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867261 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867265 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867269 | 2026/08/13 09:41:51
CSD_2 | Initial condition | 5867273 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867277 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867282 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867287 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867292 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867295 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867298 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867301 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867304 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867307 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867311 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867315 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867318 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867321 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867324 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867327 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867330 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867333 | 2026/08/13 09:41:51
CSD_3 | Initial condition | 5867336 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867340 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867343 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867347 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867350 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867353 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867356 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867359 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867362 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867366 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867370 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867373 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867376 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867379 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867382 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867385 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867388 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867391 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867394 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867397 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867400 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867403 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867406 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867409 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867412 | 2026/08/13 09:41:51
CSD_4 | Initial condition | 5867415 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867419 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867422 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867426 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867430 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867435 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867440 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867445 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867448 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867451 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867454 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867457 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867460 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867463 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867467 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867471 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867474 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867477 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867480 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867483 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867486 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867489 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867492 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867495 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867498 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867501 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867505 | 2026/08/13 09:41:51
CSD_5 | Initial condition | 5867509 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867513 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867517 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867522 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867527 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867532 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867535 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867538 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867541 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867544 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867547 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867550 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867554 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867558 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867561 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867564 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867567 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867570 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867573 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867576 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867579 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867582 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867585 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867589 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867593 | 2026/08/13 09:41:51
CSD_6 | Initial condition | 5867597 | 2026/08/13 09:41:51
CSD_1 | Option 1 | 5866825 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866829 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866833 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866837 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866841 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866843 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866845 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866848 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866851 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866853 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866855 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866857 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866860 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866862 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866864 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866867 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866869 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866871 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866873 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866875 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866877 | 2026/08/17 16:21:48
CSD_1 | Option 1 | 5866879 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866881 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866884 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866887 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866890 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866894 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866897 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866900 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866903 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866906 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866909 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866912 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866916 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866919 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866922 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866925 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866928 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866931 | 2026/08/17 16:21:48
CSD_2 | Option 1 | 5866934 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866937 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866941 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866944 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866947 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866950 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866953 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866956 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866960 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866964 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866967 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866970 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866973 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866976 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866979 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866982 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866985 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866988 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866991 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866994 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5866997 | 2026/08/17 16:21:48
CSD_3 | Option 1 | 5867000 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867003 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867007 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867010 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867014 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867017 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867020 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867023 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867026 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867029 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867033 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867037 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867040 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867043 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867046 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867049 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867052 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867055 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867058 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867061 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867064 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867067 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867070 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867073 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867076 | 2026/08/17 16:21:48
CSD_4 | Option 1 | 5867079 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867082 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867087 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867092 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867097 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867101 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867105 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867109 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867112 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867116 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867120 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867123 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867126 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867129 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867132 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867135 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867138 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867142 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867146 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867149 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867152 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867155 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867158 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867161 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867164 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867167 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867170 | 2026/08/17 16:21:48
CSD_5 | Option 1 | 5867173 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867176 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867181 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867186 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867191 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867195 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867199 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867203 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867207 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867211 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867214 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867217 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867220 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867223 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867226 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867229 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867233 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867237 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867240 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867243 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867246 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867249 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867252 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867255 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867258 | 2026/08/17 16:21:48
CSD_6 | Option 1 | 5867261 | 2026/08/17 16:21:48