## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | CSD_1-1 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pou09b88362-7125-4f03-80ea-ab39318855c4.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-170bfe019-1358-42ec-9317-da8134e5651a.png | T.O. 楼板 | hs | 51-52/D-E | 2025/04/18 16:49:00 | 10
2 | CSD_1-2 | Programme copy | 2025/04/18 17:01:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pou76ef27d5-5e2f-497e-8d13-ad687374ef08.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-28ab4c48d-8a59-4936-bc3d-4c45ac0ef092.png | T.O. 楼板 | hs | 52-53/D-E | 2025/04/18 16:49:00 | 10
3 | CSD_1-3 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pou77ac3bdc-3924-466a-be74-eb5484c30973.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-3a8789c37-3a9f-4ee0-9426-d67b64dda7ea.png | T.O. 楼板 | hs | 53-54/D-E | 2025/04/18 16:49:00 | 10
4 | CSD_1-4 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/poub39dfa64-713c-4df8-85b7-1ba23711e1d2.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-433c205bc-03b0-43bc-af68-85f2e2233fdd.png | T.O. 楼板 | hs | 54-55/D-E | 2025/04/18 16:49:00 | 10
5 | CSD_1-5 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pou711ca9df-ef3a-4a41-a4ef-42e2a81a5568.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-517b6b297-19f6-4626-bea8-c770ecc557ac.png | T.O. 楼板 | hs | 55-56/D-E | 2025/04/18 16:49:00 | 10
6 | CSD_1-6 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/poubefcd973-9ed2-4f59-ac7e-c0514f8cfc38.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-62c24385a-cf06-4307-b265-12ca46dbcddb.png | T.O. 楼板 | hs | 56-57/D-E | 2025/04/18 16:49:00 | 10
7 | CSD_1-7 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pou64240b5f-7129-4f0b-b99c-6af72f2def72.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-799e41303-eb05-40ee-b541-21153ee7248e.png | T.O. 楼板 | hs | 57-58/D-E | 2025/04/18 16:49:00 | 10
8 | CSD_1-8 | Programme copy | 2025/04/18 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pou47e235d2-8b9a-4acb-a9d2-60d91694ebd4.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-82c4321b7-456f-44e8-8c94-40e4431a1647.png | T.O. 楼板 | hs | 58-59/D-E | 2025/04/18 16:49:00 | 10
9 | CSD_1-9 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pouda140577-77cf-4cec-b19c-8377cf5fa1c1.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-99ce39835-6902-4b02-9828-a9afd97de02a.png | T.O. 楼板 | hs | 59-60/D-E | 2025/04/18 16:49:00 | 10
10 | CSD_1-10 | Programme | 2025/04/18 16:49:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/04/21 08:40:17 | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Sectional/pouc34ce3b8-fe18-465b-9adc-ea0372a38ee8.png | https://transit.szhoogo.com/d4819a79-7dd8-4cc3-8c09-8b5c0d744b86/a8debe58-8738-4a09-908b-0cdc626882b9202504210840170000/Plan/CSD_1-1077827635-4349-4241-8934-cf94189b99d7.png | T.O. 楼板 | hs | 60-61/D-E | 2025/04/18 16:49:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.