## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | CSD_1 | Programme | 2025/06/13 18:38:00 | 0 | 0 | 1 | 1 | 1 | 0 | 5 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou0276ea7b-efca-4c20-97c4-1ee17e4cfeb4.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_b29592fd-cdfe-4568-9d09-68c48292b269.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:38:00 | 10
2 | CSD_1-1 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/poue27baa0c-902d-4cf2-8243-9d33b3037823.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_62670d3d-39f7-4e81-8126-1aa843ab713e.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
3 | CSD_1-2 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou7167cc4f-3fcb-401f-86b5-77842f20a6b1.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_0f054802-171f-4984-8714-ef5344ceda59.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
4 | CSD_1-3 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou9b150670-c8fb-498d-96a0-5e9f1cc36ea5.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_e6359237-2397-4027-aa8b-7fdebe767074.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
5 | CSD_1-4 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouaf83982a-f68c-48df-af0a-3120b845b926.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_86966f69-937f-4a24-ae2a-082c35fcfb5a.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
6 | CSD_1-5 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou5add05fb-c7ad-4524-b54c-37f6499d8831.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_18e44bd4-bc8c-4d40-bda8-3e171b525690.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
7 | CSD_1-6 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouee42fa1e-8bce-4bed-8f1d-80430c4ad33c.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_6c9ec448-129c-443c-983b-d4073918ec16.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:40:00 | 10
8 | CSD_1-7 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/poub7d12dc6-8d13-4b15-b485-f921584fafd2.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_2289090d-ac6e-4a74-939d-50d9118c54ba.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:40:00 | 10
9 | CSD_1-8 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouf043f16c-85ed-487c-9853-a6291aecdda5.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_6cfe104e-51bd-4d33-b5f1-24911b5753bf.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:40:00 | 10
10 | CSD_1-9 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouf85e931a-9ead-43fc-9fb7-7de7a03c03df.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_e797cf3c-134e-4d04-a63f-4355964227ac.png | Platform Level | (none) | 8-9/A-B | 2025/06/13 18:40:00 | 10
11 | CSD_1-10 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouc755c342-3b47-4a2d-96e8-ab5713feda09.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_d2567bd0-5daa-4491-8799-088d1e0640e3.png | Platform Level | (none) | 8-9/A-B | 2025/06/13 18:40:00 | 10
1 | CSD_1 | Programme | 2025/06/15 10:32:00 | 0 | 0 | 4 | 4 | 1 | 0 | 9 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/pou77b10e96-c61a-4414-af38-b24c37c0b94a.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_d52fb4b5-c0d3-4486-ab7e-066e101f8d10.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:32:00 | 10
2 | CSD_2 | Programme | 2025/06/15 10:38:00 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/pou11657705-2d28-41d6-9189-45c77ce53f0c.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_ecaa998e-5acc-4446-bc43-9efb1907bfaf.png | Platform Level | (none) | 14-15/A-B | 2025/06/15 10:38:00 | 10
3 | CSD_3 | Programme | 2025/06/15 10:40:00 | 0 | 0 | 1 | 1 | 1 | 0 | 5 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poucce39a2c-a900-4b37-bbdb-880a1af4f23c.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_db80a2f1-a12a-41c2-adf9-a88586f4f6bc.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:40:00 | 10
4 | CSD_3-1 | Programme | 2025/06/15 10:43:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poub87e0271-2a7b-45f4-8b65-e18aea8f70ed.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_19327af5-431d-4d2a-a076-456f5032a6af.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:43:00 | 10
5 | CSD_3-2 | Programme | 2025/06/15 10:43:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/pou17f043ca-12e9-4d85-ba68-d5ca66c936fc.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_76b7332b-7154-4c1c-90d0-1bdaa79ef41f.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:43:00 | 10
6 | CSD_3-3 | Programme | 2025/06/15 10:43:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poue65f9fe6-5e4e-44c4-8a78-75e6d6fb011e.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_eb1893e7-ea9b-4c14-990f-2ab96fbdd131.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:43:00 | 10
7 | CSD_3-4 | Programme | 2025/06/15 10:43:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/pou4d37a427-feef-46b2-a97f-a7dcae10bed8.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_9e00b7ce-59d4-4c49-80df-abfa14a20943.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:43:00 | 10
8 | CSD_3-5 | Programme | 2025/06/15 10:43:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/pou24d93af9-7626-415e-8491-38a2a9442030.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_88857668-f5f7-4c15-99db-77cb7b204090.png | Platform Level | (none) | 7-8/A-B | 2025/06/15 10:43:00 | 10
9 | CSD_3-6 | Programme | 2025/06/15 10:44:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/pou884be7bc-a46a-48f4-89d1-cba8be95ff67.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_d8a3ed30-84db-4f67-92ab-0f8ec4f5ee54.png | Platform Level | (none) | 8-9/A-B | 2025/06/15 10:44:00 | 10
10 | CSD_3-7 | Programme | 2025/06/15 10:44:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poub037a332-87e4-4938-84cf-c301feba9e4a.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_82d00b70-d7c2-4483-9914-a17f259ce25a.png | Platform Level | (none) | 8-9/A-B | 2025/06/15 10:44:00 | 10
11 | CSD_3-8 | Programme | 2025/06/15 10:44:00 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poufe286314-e1b7-4fd2-9df4-8876f1f22afc.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_1f7825f7-7c13-42b9-a595-e5d0e11e1eb9.png | Platform Level | (none) | 8-9/A-B | 2025/06/15 10:44:00 | 10
12 | CSD_3-9 | Programme | 2025/06/15 10:44:00 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poufcd7a3d3-5acb-43cb-9874-5f02d9739783.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_081f9ee1-02d3-410c-a3b1-5e9c5f6596ca.png | Platform Level | (none) | 8-9/A-B | 2025/06/15 10:44:00 | 10
13 | CSD_3-10 | Programme | 2025/06/15 10:44:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025/06/15 10:51:58 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Sectional/poufc996e4c-f89f-4199-a276-098d1d7c32ec.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/a29feaf8-e085-4555-a330-e02f65b49362202506151051580000/Plan/pin_05066486-0d01-4f20-94c2-8fb285940454.png | Platform Level | (none) | 8-9/A-B | 2025/06/15 10:44:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.