## Sheet1
碰撞详情
序号A | 剖面号 ID | 方案号 ID | 方案创建时间 Time | 结构碰撞数 ST | 建筑碰撞数 AR | 各自管线碰撞数 MEP | 各自管线保护框 碰撞数 MEP | 管线与风管碰撞数 AC | 低于净空控制线 HR | 管线与支架碰撞数 SS | 特殊剖面 CBWD | 上传时间 | 剖面图 | 平面图 | 楼层 Level | 区域 Region | 剖面位置 Location | 剖面创建时间 Time | 当前管综设计协调状态 State
1 | CSD_1 | Programme | 2025/06/13 18:38:00 | 0 | 0 | 1 | 1 | 1 | 0 | 5 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou0276ea7b-efca-4c20-97c4-1ee17e4cfeb4.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_b29592fd-cdfe-4568-9d09-68c48292b269.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:38:00 | 10
2 | CSD_1-1 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/poue27baa0c-902d-4cf2-8243-9d33b3037823.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_62670d3d-39f7-4e81-8126-1aa843ab713e.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
3 | CSD_1-2 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou7167cc4f-3fcb-401f-86b5-77842f20a6b1.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_0f054802-171f-4984-8714-ef5344ceda59.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
4 | CSD_1-3 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou9b150670-c8fb-498d-96a0-5e9f1cc36ea5.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_e6359237-2397-4027-aa8b-7fdebe767074.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
5 | CSD_1-4 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouaf83982a-f68c-48df-af0a-3120b845b926.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_86966f69-937f-4a24-ae2a-082c35fcfb5a.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
6 | CSD_1-5 | Programme | 2025/06/13 18:39:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pou5add05fb-c7ad-4524-b54c-37f6499d8831.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_18e44bd4-bc8c-4d40-bda8-3e171b525690.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:39:00 | 10
7 | CSD_1-6 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouee42fa1e-8bce-4bed-8f1d-80430c4ad33c.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_6c9ec448-129c-443c-983b-d4073918ec16.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:40:00 | 10
8 | CSD_1-7 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/poub7d12dc6-8d13-4b15-b485-f921584fafd2.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_2289090d-ac6e-4a74-939d-50d9118c54ba.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:40:00 | 10
9 | CSD_1-8 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouf043f16c-85ed-487c-9853-a6291aecdda5.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_6cfe104e-51bd-4d33-b5f1-24911b5753bf.png | Platform Level | (none) | 7-8/A-B | 2025/06/13 18:40:00 | 10
10 | CSD_1-9 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouf85e931a-9ead-43fc-9fb7-7de7a03c03df.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_e797cf3c-134e-4d04-a63f-4355964227ac.png | Platform Level | (none) | 8-9/A-B | 2025/06/13 18:40:00 | 10
11 | CSD_1-10 | Programme | 2025/06/13 18:40:00 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 2025/06/13 18:51:09 | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Sectional/pouc755c342-3b47-4a2d-96e8-ab5713feda09.png | https://transit.szhoogo.com/d4c1b60d-597e-4e21-a463-0b74b66e3ec7/8b140503-43e8-4d57-b445-b626cbc35d0f202506131851090000/Plan/pin_d2567bd0-5daa-4491-8799-088d1e0640e3.png | Platform Level | (none) | 8-9/A-B | 2025/06/13 18:40:00 | 10

## Sheet2
| 0 | 1 | 2 | 3
0 | 状态 0：生成CSD BIM模型的剖面排布图，对MiMEP的可建造性进行核对。 | 团队内部仅完成剖面生成 | 团队内部已分析剖面情况 | 已把有问题的剖面汇报给项目组
1 | 状态 1：剖面排布图发送給各专业工程师进行协调和标注。 | 剖面仅发送给专业工程师 | 剖面已和专业工程师开会讨论 | 剖面已获得专业工程师的方案批复
2 | 状态 2：剖面排布协调已验证，进行局部CSD BIM建模。 | 剖面已验证，需要重来 | 剖面已验证，需要提疑 | 剖面已验证，原则上可行
3 | 状态 3：MiMEP框架在创建剖面位置进行建模，以便各专业工程师之间进行进一步协调以进行微调。 | 剖面位置的框架仅建模无分析 | 剖面位置框架建模后需调整方案 | 剖面增加框架模型后可行
4 | 状态 4：CSD模型经过修改、更新和冻结，可移交开始MiMEP模块建模。 | CSD模型已修改未审核 | CSD模型已修改并调整框架模型 | CSD模型已增补非几何信息并冻结移交
| 0 | 1 | 2 | 3
0 | Status 0: Section Drawings of CSD BIM model are generated and check with MiMEP constructability. | Within the team, only the generation of section has been completed. | The team has analyzed the section situation internally. | The problematic section has been reported to the project team.
1 | Status 1: Section Drawings send to trade engineers for coordination and markup. | The section is only sent to professional engineers. | The section has been discussed in a meeting with professional engineers. | The section has been approved by a professional engineer's proposal.
2 | Status 2: Section coordination is vertified and CSD BIM Model is partially modelling. | The section has been validated and needs to be redone. | The section has been verified and needs to be questioned. | The section has been verified and is feasible in principle.
3 | Status 3: MiMEP framing is modelled in critical sections for further coordination amongst trade engineers to fine-tuning. | The framework for the section position only includes modeling without analysis. | After modeling the section position framework, the plan needs to be adjusted. | Feasibility after adding a framework model to the section.
4 | Status 4: CSD model is revised, updated and frozen for MiMEP module modeling. | CSD model has been modified but not yet reviewed. | The CSD model has been modified and the framework model has been adjusted. | The CSD model has been supplemented with non geometric information and frozen for transfer.